## Daily
SN | Task | Description | Frequency | Start Date | End Dtae | Status | Remarks | Owner
1 | POC Sheet update | Follow Up | Daily | NA |  | On going |  | Ahmed
2 | POC Project Update | Follow Up | Daily | NA |  | On going |  | Ahmed
3 | FAB Cases | Follow Up | Daily | NA |  | On going |  | Ahmed
4
5

## General Tasks
Task | Priority | Description | Start Date | ETA | End date | Owner | Status | Remarks
AMC Details |  | All AMC support details to be gathered | 2024-06-11 |  |  | Venkat
Niagara networks guide |  |  | 2024-08-01 |  |  | Nasif
Certification's Validation |  | For Disti Rebates | 2024-08-21 |  |  | Venkat
DNS Proxy Lab - Need to prepare a internal guide |  |  | 2024-10-09 |  |  | Salman
Air gap license |  |  | 2024-11-04 |  |  | Venkat
EC-XS devices power cable to be retrieved and assign labels | High |  | 2024-12-20 |  |  | Nasif
LMG LLD Document preparation for territory(HO) wise |  |  | 2025-05-14 | 2026-01-08 |  | Ahmed | Completed | All territory HO doucments are in progress fine tunning remaining (19th feb)
Demo arrya lab to host a webserver |  |  | 2025-10-25 |  |  | Nasif | Ongping
EC-L Device which came from Aruba needs to be shipped back to Aruba |  |  | 2025-09-01 |  |  | Nasif | Ongoing | To identify the serial number from inventory
Device to be arranged for easy tracking |  |  | 2025-09-10 |  |  | Nasif | Ongoing | to check with adarsh
Lmg Non-UAE/KSA region secondary hub location to be discussed. |  |  | 2025-09-10 |  |  | Ahmed | Ongoing | To be discussed with LMG team. (19th feb)
IPS/IDS events to sent to splunk |  |  | 2025-09-10 |  |  | Nasif | Ongoing
to check for Syslog server to implement on our setup |  |  | 2025-09-10 |  |  | Nasif | Ongoing
Link bandwidth to be verified on LMG |  |  | 2025-09-10 | 2026-01-04 |  | Ahmed/Afsal/Nasif | Ongoing | Need to check on the bandwidth configured on devices and utlization on the stats, need to verify on BOQ also
NetAlly Training |  | Need to connect with NetAlly team for LAB | 2025-09-11 |  |  | Nasif |  | Need to connect with Darayus for training videos, need to prepeare an session on 9th Jan
LMG Migration Details to be regularly updated on the GULFIT tracker | Medium |  | 2025-09-19 | 2026-01-04 |  | Nasif | Ongoing | After ramadan change freeze migrations will resume
ISP Names to be Mapped on all migrated LMG Sites |  | For existing and old sites | 2025-09-19 | 2026-01-10 |  | Ahmed/Afsal/Nasif | Ongoing | Need to fill for Existing and old sites, On SOP document this thing should be added, Shared excel sheet to sakib to fill the ISP names. sent mail to sakib on feb 19th
To check with adarsh for space to keep the EC devices safely
OT Calculation sheet to be prepeared |  |  | 2025-12-10 |  |  | Nasif | Yet to start
NFR EC-XS RMA Issue |  |  | 2025-12-15 |  |  | Nasif | Ongoing | Need to follow up with shijeesh, cal
Naivas project phase -2 update/ HO LLD Validation (VRRP, physical connectivity between EC and switch, addition of new ISP on the WAN, Spoke to spoke communication block. |  | Prepeared and kept ready | 2025-12-15 |  |  | Nasif | Ongoing | Call has been scheduled on 23rd feb
Leave planning sheet |  |  | 2025-12-16 |  |  | Nasif | Ongoing
Alibaba cloud |  |  | 2025-12-16 |  |  | Nasif/Afsal
Aruba devices to be shipped back from sechpoint | Medium |  | 2025-12-17 |  |  |  | ongoing | Nasif visited sechpoint and confirmed 2 devices are in sechpoint. awaiting aruba customer to ship the devices. (19th feb 26)
LMG HLD and LLD modifications for UAE DC | Medium |  | 2025-12-23 | 2026-01-08 |  | Ahmed | Yet to start | Venkat to advise for Bwan1 interface on deployment page for both EC1 and EC2
Naivas HLD for phase 2 to get validated from NAIVAS team | Medium |  | 2025-12-24 |  |  | Nasif | Completed | Shared to customer and waiting for response
Naivas phase 1 sign off document | Medium |  | 2025-12-24 |  |  | Ahmed | Ongoing
Burjeel POC devices to follow up-every tuesday and friday | [7 empty] | Branch/DR collected currently in GULFIT office, DC device waiting for confirmation, last mail sent on 4th feb
Backhaul setup for LMG KSA if internet link goes down | Medium |  | 2025-12-28 |  |  | Ahmed | Ongoing | Venkat to advise on the backhaul design
DR setup for LMG between kuwait,qatar and Riyadh | Medium |  |  |  |  | Salman | on going | LMG to configure similar routes setup as compare to Riyadh heaf office. Nagraj to discuss and confirm the timeframe to do the changes
Device shipment back to aruba need to send remainder mail on 10th March, every two weeks needs to send reminder | [6 empty] | on going | Email sent on last 24th feb
FAB Gift city device, nasif to follow up with vishnu on daily basis | [7 empty] | Last followed up on 24th feb
DH NON CORP La mer south Migration | [5 empty] | Nasif | Ongoing | Need to check with venkat on feb 23rd
To check and change the gateways of netsec ESXI servers. |  |  | 2026-02-19
To do the Labeling on the cables |  |  | 2026-02-19
NetAlly demo session on thursday 26th feb 11-12 by nasif to venkat meeting invite to be shared |  |  | 2026-02-19 |  |  |  |  | First session completed about auto testing need to do a documentation about it.
Sempris DSP Course to be completed march 10th for afsal |  |  | 2026-02-19 |  |  |  |  | Completed by nasif
LMG LLD Five sites from each region to be prepeared |  |  | 2026-02-19 |  |  | Nasif/Afsal |  | Need to check with venkat if it has to be done for all the sites or five each , Nasif completed Dammam 5 sites,
Aruba SDWAN Pre-Config / YAML Testing |  |  | 2026-02-24 |  |  | Ahmed | Completed | Test completed by ahmed document need to prepeare by nasif
Pre configure appliance in aruba documentation |  |  | 2026-02-25 |  |  | Nasif/Afsal
Moving Axis connector to different VM |  |  | 2026-02-27 |  |  | Nasif |  | New VM deployed in VM.109 and old one is disabled in axis.
Excel sheet to be prepeared to get the LAN and Device IP details for LMG |  |  | 2026-02-27 |  | 2026-03-10 | Nasif |  | Completed and shared to Ahmed/venkat
Project time tracker sheet Weekly total hours update |  |  | 2026-03-05 |  |  | Nasif/Afsal |  | Has setup automation and will automatically update
ADAA need to follow up with Muatez for payment |  |  | 2026-03-16 |  |  | Nasif

## Weekly
SN | Task | Description | Frequency | Start Date | End Dtae | Status | Remarks | Owner
1 | Inventory (SP/CATO/CL/NN/ARRAY) | Need to update Weekly | Weekly | NA |  | On going |  | Ahmed
2 | POC Device Retrieval | Follow Up | Weekly | NA |  | On going
3 | FAB Tunnel down troubleshootinhg | Need to check with Dinesh for availablity | Weekly |  |  | On going
4 | PROJECT DETAILS | Need to update sheet weekly
5
6

## Monthly
SN | Task | Description | Frequency | Start Date | End Dtae | Status | Remarks | Owner
1 | OT Sheet | All Engineers to submit the OT sheet by 3rd of every month
2 | Bckup of sheets
3
4
5

## Quarterly
SN | Task | Description | Frequency | Start Date | End Dtae | Status | Remarks | Owner
1 | FAB Quarter Health Check | Need to perform health check every quarter | Quarter |  |  | On going | Currently NO AMC | Ahmed
2
3
4
5

## General Tasks - Completed
Description | Priority | Descripton | Start Date | ETA | End Dtae | Owner | Status | Remarks
Need to trouble shoot LD8 | [5 empty] | Ahmed | Completed
Need to check for IBGP Need to check BGP timer Need to check the VRRP | [5 empty] | Ahmed | Completed
IPSEC tunnel check between Cisco router and Silverpeak |  |  | 12th Oct |  |  | Ahmed | completed | Form IPSEC IKEV1 tunnel between silverpeak and cisco router, Phase 1 tunnel came up, phase 2 is down since no data is transferring over phase 2 tunnel-- Need to generate traffic between PCs and check
Prepare LLD Document Template |  |  | 45217 |  |  | Salman | Completed
Need to deploy 3rd Orchestrator |  |  | 45271 |  |  | Ahmed | Completed
Need to check VRRP in lab for CBUAE |  |  | 45271 |  |  | Ahmed | Completed
Activity completed and report submitted |  |  | 2024-05-24 |  |  | Ahmed | Completed
ADAFSA modified Visio diagram |  |  | 2024-05-31 |  |  | Ahmed | Completed
Customer is able to do winscp to EC |  |  | 2024-05-31 |  |  | Ahmed | Completed
|  |  | 2024-06-01 |  |  | Ahmed | Completed
Shared |  |  | 2024-06-07 |  |  | Ahmed | Completed
Switches mounted | [5 empty] | Ahmed | Completed
30th june getting expire |  |  | 2024-06-05 |  | 2024-06-05 | Venkat | Completed | License extended till 30th dec 2024
Awaiting for SE confirmation |  |  | 2024-06-05 |  | 2024-06-19 | Venkat | Completed | Orch 9.2.10 & ECOS 9.1.4.4 ( for time being untill all ecos is above 8.3.20)
TS oci tunnel |  |  | 2024-06-05 |  | 2024-06-06 | Venkat | Completed
Ahmed to perform this activity scheduled on June 9th 2.30 pm |  |  | 2024-06-06 |  |  | Ahmed / Nasif | Completed
Prepare the diagram for Mowasalat PoC |  |  | 2024-06-06 |  | 2024-06-07 | Nasif | Completed
Send mail to mowaslat |  |  | 2024-06-11 |  | 2024-06-12 | Venkat | Completed
Orch upgraded to 9.3.3 |  |  | 2024-06-06 |  |  | Ahmed | Completed
Arrange the power adapter |  |  | 2024-06-19 |  |  | Nasif | completed | device powering on
Work on the existing tech/Sow document |  |  | 2024-06-19 |  |  | Nasif | completed
OCI Test |  |  | 2023-10-26 |  |  | Salman | Completed | Need to test the ENBD OCI setup
Aruba PS + AMC Support Details Sheet to be created |  |  | 2024-07-05 |  |  | Nasif | Completed
Dhofar bank report |  |  | 2024-07-03 |  |  | Nasif | Completed
ENBD CIFS Case |  | TAC requested call with customer | 2024-06-05 |  |  | Ahmed | Completed | customer not responded after the last session
bridge works document preperation |  | need to validate | 2024-07-26 |  | 2024-09-01 | Nasif | Completed
Mednet devices need to follow up |  |  | 2024-07-09 |  |  | Nasif | Completed | aruba team will follow up
Aruba SSE Certification |  |  | 2024-08-26 |  | 2024-09-09 | Nasif | Completed
DFM Technical Proposal |  |  | 2024-07-09 |  | 2024-07-11 | Ahmed | Completed
Deploying new SSE connector in lab |  | lab | 2024-09-09 |  | 2024-09-10 | Nasif | Completed
Prepeare document to avoid misconfiguration for DH |  |  | 2024-09-17 |  |  | Nasif | Completed
SSE Azure AD deployment guide |  |  | 2024-09-20 |  | 2024-09-23 | Nasif | Completed
DH Sites BW Sheet |  |  | 2024-08-29 |  |  | Nasif | Completed
PORTrockIT testing |  |  |  |  | 2024-08-26 | nasif | Completed
Build new hardware with vmware for additonal capacity |  |  | 2024-09-06 |  |  | Ahmed | Completed
Task Sheet for FAB |  | All information re
FAB OS Version Validation |  | Hiub 8.3.6.2 & Spoke sites 9.2 tested but as per SE he informed to go with 9.3 for EC appliances; awaiting for his confirmation |  |  |  | Nasif | Completed
FAB Tunnel Down - Follow up FAB team |  | Need to check with Dinesh, awaiting dinesh availablity | 2024-06-05 |  |  | Ahmed | Completed
ADAFSA Shipment |  | Device to be shipped post confirmation | 2024-06-04 |  |  | Nasif |  | As per venkat we are not shipping waiting for confirmation
FAB Orchestrator upgrade doc |  |  | 2024-06-12 |  |  | Ahmed | Completed
Aruba HLD Standard Format |  |  | 2024-07-01 |  |  | Ahmed | Completed
Dedicated Aruba lab full use cases |  | DEMO lab migrated to .150 orchestrator | 2024-07-04 |  |  | Ahmed | Completed
FAB Case Tracker for AMC |  |  | 2024-07-09 |  |  | Venkat/Ahmed | Completed
CATO-Internal KT session |  |  | 2024-07-11 |  |  | Ahmed | Completed
Prepare the appliance backup as a reference document and upload to gulfit online |  | TAC provided certain infos. related to FAB case | 2024-08-20 |  |  | Ahmed | Completed
Prepare Naivas Tech document |  |  | 2024-08-20 |  |  | Ahmed | Completed
NEDC Tech Document |  |  | 2024-09-12 |  |  | Ahmed | Completed
SoW - Master Copy - Validation |  |  | 2024-10-09 |  |  | Ahmed | Completed
AMC contract document master copy need to prepeare |  |  | 2024-10-21 |  |  | nasif | Completed
Validate with Omni Jimmy for As built document |  | every two weeks follow up | 2024-06-11 |  |  | Nasif | Completed | waiting for confirmation from D.H team
Follow up for TVH PoC devices with Philip charles and retrieve to gulfit office |  | Devices are in Qatar office with Philip | 2024-08-19 |  |  | Ahmed | Completed | connected with pramod and fctory reset done on two devices
HLD master Document fine tuning |  |  | 2024-11-07 |  | 2024-11-13 | nasif | Completed
Orchestrator Hard Disk Expansion Doc. |  |  | 2024-12-13 |  |  | Nasif | Completed
DFM Tracker sheet to prepeare |  |  | 2024-11-15 |  |  | Nasif | Completed
Migrate remote users to axis security from cato |  |  | 2024-12-27 |  | 2024-12-27 | Ahmed | Completed
Migrate Gulf IT lab from cato to edgeconnect on gulfit cloud orchestrator |  |  | 2024-12-27 |  | 2024-12-27 | Ahmed | Completed
UAT document for DFM |  |  | 2024-12-24 |  | 2024-12-27 | Ahmed | Completed
KUWAIT DEVICE RETRIEVAL FROM RANA |  |  | 2025-01-02 |  |  | Nasif | Completed
Splunk integration with orchestrator and edgeconnct document |  |  | 2025-06-03 |  | 2025-06-04 | Nasif | Completed | document sent to venkat and uploaded in share drive
Aruba LLD Standard Format |  |  | 2024-07-01 |  |  | Ahmed | Completed
Aruba Customer list |  | list prepeared need to sort according to region | 2024-07-04 |  |  | Nasif | Completed
Review Aruba HLD prepared by ahmed |  |  | 2024-07-05 |  |  | Venkat | Completed
Review SoW doc prepared by third party team |  |  | 2024-07-05 |  |  | Venkat | Completed
Mashreq Technical workshop details |  |  | 2024-07-25 |  |  | Prasanth | Completed
Mashreq Technical workshop Questionnaire |  |  | 2024-07-25 |  |  | Prasanth | Completed
0rchestrator HA |  |  | 2024-11-11 |  |  | nasif | ongoing
LMG Cloud Device Follow Up |  |  | 2024-11-15 |  |  | Venkat | Completed | LMG Went with their native cloud connectivity with vodafone
AZURE EC DEPLOYMENT |  |  | 2025-01-06 |  |  | Nasif | Completed
Devices in Qatar to be shipped back to Saudi |  |  | 2025-09-02 |  |  | Nasif | Completed | Device from SRC used for AMEX POC so not required to ship from Qatar.
Kemri SDWAN device upgradation |  |  | 2025-09-10 |  |  | Nasif | Completed
Kemri Diagram Preperation |  |  | 2025-09-22 |  |  | Nasif | Completed
3 - EC-XS devices to be ready for shipping to nigeria | Medium |  | 2025-09-30 |  |  | Nasif | Completed | Devices to be shipped to nigeria
DH Non corp Migration Date Inventory sheet |  | To keep track of devices and details | 2025-12-08 |  |  | Nasif | Completed | Completed and uploaded in sharedrive under Non corp folder
LMG Orch spec validation with Aruba |  | Case Number 20250924-440299 | 2025-09-23 |  |  | Nasif | Ongoing | TAC Response: This cloud orch deployed with large deployment size which can hold from 200 - 1000 appliances in total.
QDSBG Sysdumps to be uploaded for the appliances | Medium |  | 2025-12-17 |  |  | Nasif | Completed
DH-NC Dec18th 3:00 AM - 5:00 AM there will be power outage Need to support in case needed | Medium | [6 empty] | Activity completed
Naivas LLD to be prepeared |  |  | 2025-09-09 |  |  | Nasif | Completed | To be copied from skeleton docs
DH Devices validation |  |  | 2025-12-16 |  |  | Nasif | Completed | Validated
DH NC Diagrams to be sent to suheb | Medium |  | 2025-12-24 |  | 2025-12-24 | Nasif | Completed | Document shared to suheb dh via mail
DH Last exit dubai initial configuration |  |  | 2025-12-15 |  | 2025-12-26 | Nasif | Completed
To prepeare an Excel sheet for links to different internal documents in one place |  |  | 2025-12-16 | 2026-01-07 |  | Nasif | Completed | Shared to venkat
Production device to be swapped with demo setup device |  |  | 2025-09-10 | 2025-01-02 |  | Nasif | Completed | Need to confirm and fill in the inventory
LMG LLD UAE Branches and Pilot sites |  |  | 2025-09-01 |  |  | Ahmed | completed | Submitted to LMG
LMG HLD including all territory |  |  | 2025-05-14 |  |  | Ahmed | Completed | Submitted to LMG
LMG LLD Document preparation including jordan, bahrain, warehouses and pilot sites |  |  | 2024-10-30 |  |  | Ahmed | Completed | Submitted to LMG
LMG HLD for UAE KSA Document preparation |  |  | 2024-07-03 |  |  | Ahmed | Completed | Submitted to LMG
DH Non Corp Devices visibility in orchestrator as shaded | Medium |  | 2026-01-02 |  |  |  |  | When we opened the orchestrator to check the issue it was not greyed out because someone has changed the security policy on Nov-27-25 which allowed the traffic to reach silerpeak and orchestrator.Collected logs and prepeared document with the screenshots of the flows, to monitor until 12th
LMG Kuwait salmiya and Qatar rayan mall, bahrain marina mall boost license to be reconfigured |  |  | 2025-09-30 | 2026-01-02 |  | Ahmed | completed | Confgured and completed
La mer south initial Config | Medium |  |  |  |  | Nasif | Yet to start | Completed need to plan for migration
MOH technical proposal document | Medium |  | 2025-01-08 |  |  | Nasif | Ongoing | Prepeared and uploaded in share drive
Qassim Universitytechnical proposal document | Medium |  |  |  |  | Nasif | Ongoing | Prepeared and uploaded in share drive
DH hatta roxy cinema not visible in the orchestrator | [7 empty] | Site has been abondoned
VM Cleanup and Demo setup standardizing | Medium |  | 2026-01-23 |  |  | Nasif | Ongoing
Naivas Orchestrator Slowness. | Medium
LMG Rollout Aruba SOP to be updated and discussed with Venkat | High |  | 2025-12-17 | 2026-01-03 |  | Ahmed | completed | Venkat to review and connect if any further modifications needed
Case with Aruba for LMG on BGP configs not getting saved | High |  | 2025-12-23 |  |  | Ahmed | Completed | in cognoto mode configurations are getting saved seems to be a browser issue.
Peer priority to be configured on LMG UAE/KSA Sites |  |  | 2025-09-10 | 2025-12-29 |  | Ahmed | Ongoing | KSA and UAE is completed
Naivas - spoke to spoke communication block | High | Need to check with ahmed | 2025-12-29 | 2026-01-02 |  | Ahmed | Ongoing | Post call with shijeesh, We need to restrict the policies on device level and check the behaviour, Inter store communication blocking showcased to naivas team, now they need to implement it during non-prod hours.
LMG Solarwinds device showing down on BAH/JOR Dec 10th | High |  | 2025-12-17 |  |  | Ahmed | Completed
To setup the Darayus demo Lab |  |  | 2026-02-19 | 2026-02-24
KWT Devices onboarding and upgradation | Medium |  |  |  |  | Nasif | Ongoing | 8 Sites completed need to connect for the remaining devices, need to follow up with sakib
To setup the customer Lab |  |  | 2026-02-19
DH-NON CORP LLD DOCUMENT | High |  | 2025-09-01 |  |  | Nasif | Completed

## General Tasks - Not Completed
SN | Description |  | Start Date | End Dtae | Owner | Status | Remarks
1 | ClearPass Test | Integration of ClearPass and SDWAN solutions |  |  | Ahmed | On going
2 | FAB KZD/TCN INTL EC Replacement | Discuss with FAB team for replacement | 2023-12-19 |  | Venkat | On going
3 | DH LLD Doc. | Prepare the LLD |  |  | Ahmed/salman | On going
4 | DH As Built | As Built document has to be prepared for migrated sites |  |  | Nasif | On going | Salman to send mail to jimmy for validating previous shared as built document
5 | DH Application List Validation | Verify the Application list created for DH |  |  | Ahmed / Nasif | On going
6 | DH Address Group Validation | Duplicate entries to be validated in address group for DH |  |  | Ahmed / Nasif | On going
7 | Upload DH files to Aruba Account |  | 2024-06-01 |  | Nasif | On going
| DH-NC-Citywalk slowness in accessing devices | High |  | 2025-12-16 |  |  | Venkat | Ongoing | Need to connect with them and check
36 | QDSBG - File share access across the network is slow | High |  | 2025-12-17 |  |  | Nasif | Ongoing | BIO has to be fine tuned, Need to put optimzable traffic in the Critical apps and enable boost only for that and remove from default and realtime. Requested Client's availability on Tuesday 13th jan.